VEHICLE SALES AND MANAGEMENT SYSTEM

COMPLETE PROJECT CHART / PROJECT SCHEDULE

University Group Project • September 2026

| Item | Details |
| --- | --- |
| Project Name | Vehicle Sales and Management System (VSMS) |
| Project Type | Software Engineering / University Group Project |
| Project Purpose | Develop a dealership system for managing vehicles, inventory, customers, reservations, sales, payments, employees and reports. |
| Planned Duration | 12 weeks |
| Development Approach | Iterative and incremental development |
| Team | Ahmadullah Hayat, Ehsanullah Habib, Hewad Shams, Haroon Faizi |
| Main Stakeholders | Administrator, Manager, Salesperson, Customer, Project Team and Instructor |

# 1. Project Objectives

Define clear requirements and project boundaries for VSMS.

Produce a professional SRS and consistent UML/database models.

Design and implement vehicle inventory, customer, reservation, sales and payment workflows.

Provide role-based access for Administrator, Manager and Salesperson.

Develop and integrate the frontend, backend and relational database.

Test the system against approved requirements and acceptance criteria.

Prepare the final report, screenshots, source code/database package and presentation.

# 2. Project Phases and Outputs

| # | Phase | Main Output |
| --- | --- | --- |
| 1 | Project Initiation | Problem, objectives, stakeholders and scope |
| 2 | Project Planning | Project chart, responsibilities, schedule and risks |
| 3 | Requirements Engineering | Functional/non-functional requirements, actors and business rules |
| 4 | SRS Preparation | Complete Software Requirements Specification |
| 5 | System Analysis & Modeling | Use Case, Activity, Class and Sequence models |
| 6 | Database Analysis & Design | Entities, attributes, ER diagram and normalization |
| 7 | System/UI Design | Architecture, navigation, permissions and wireframes |
| 8 | Implementation | Frontend, backend, database and business modules |
| 9 | Integration | Integrated frontend, backend and database |
| 10 | Testing & Validation | Unit, integration, system, security and usability testing |
| 11 | Documentation | Updated SRS, report, screenshots and technical documentation |
| 12 | Presentation & Submission | Final review, demonstration and submission |

# 3. Team Responsibilities

| Member / Role | Primary Function | Main Tasks |
| --- | --- | --- |
| Ahmadullah Hayat — Project Lead / Analyst | Project management, requirements, SRS and coordination | Problem/objectives/scope; requirements coordination; business rules; SRS; acceptance criteria; reports; coordination; final documentation |
| Hewad Shams — Functional / Business-Workflow Lead | Use cases, functional workflows and core business modules | Use cases/descriptions; authentication/authorization workflow; vehicle/customer/reservation/sales workflows; core implementation |
| Haroon Faizi — Database / Backend Lead | Database, backend services and data models | Data support; class/sequence support; entities/ERD/normalization; database setup; payment; backend services; integration support |
| Ehsanullah Habib — UI / Integration / QA Lead | UI, navigation, integration support and test coordination | Activity diagrams; wireframes/navigation; UI screens; integration support; test cases; testing coordination; usability/security test support |
| All Members — Collaboration & QA | Review, testing and final delivery | Peer review; integration; functional/integration/security/usability testing; bug fixing; final presentation |

# 4. Responsibility Rules Used

Each task has one clear primary owner or a clearly named support pair/team.

Requirements and SRS work are led by the Project Lead/Analyst.

Use-case and business-workflow work is led by the Functional/Business-Workflow Lead.

Database/backend work is led by the Database/Backend Lead.

UI, integration support and test coordination are led by the UI/Integration/QA Lead.

Testing is a shared team responsibility, with Ehsanullah coordinating test preparation and QA.

Milestone owners are aligned with the detailed tasks they lead.

Dependencies point to work that logically must be completed first.

# 5. Detailed Project Schedule:

| ID | Phase | Task / Activity | Deliverable | Responsible | Dependency | Days | Start | End | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Initiation | Define problem and project idea | Problem statement | All | — | 1 | W1 | W1 | Completed |
| 2 | Initiation | Define project objectives | Project objectives | Ahmadullah | 1 | 1 | W1 | W1 | Completed |
| 3 | Initiation | Identify stakeholders and actors | Stakeholder/actor list | Ahmadullah + Hewad | 1 | 1 | W1 | W1 | Completed |
| 4 | Initiation | Define project scope and boundaries | Approved scope | Ahmadullah + All | 1–3 | 2 | W1 | W1 | Completed |
| 5 | Planning | Prepare project chart and work plan | Project chart | Ahmadullah | 4 | 2 | W1 | W1 | Completed |
| 6 | Requirements | Gather functional requirements | Functional requirements | Ahmadullah + Hewad | 4 | 3 | W1 | W2 | Completed |
| 7 | Requirements | Gather non-functional requirements | NFR list | Ahmadullah + Ehsanullah | 6 | 2 | W2 | W2 | Completed |
| 8 | Requirements | Define business rules | Business rules | Ahmadullah + Hewad | 6 | 2 | W2 | W2 | Completed |
| 9 | Requirements | Identify actors and use cases | Use-case list | Hewad | 6 | 2 | W2 | W2 | Completed |
| 10 | SRS | Write Introduction and Overall Description | SRS Sections 1–2 | Ahmadullah + Hewad | 6–9 | 3 | W2 | W3 | Completed |
| 11 | SRS | Write Specific Requirements | FR/NFR/interface requirements | Ahmadullah + Hewad | 7–10 | 4 | W3 | W4 | Completed |
| 12 | SRS | Write Data Requirements and Constraints | Data/constraint sections | Ahmadullah + Haroon | 8–11 | 2 | W4 | W4 | Completed |
| 13 | SRS | Define acceptance criteria | Acceptance criteria | Ahmadullah | 11 | 1 | W4 | W4 | Completed |
| 14 | SRS | Review and finalize SRS | Approved SRS v1.0 | All | 10–13 | 2 | W4 | W4 | Completed |
| 15 | Analysis | Create Use Case Diagram | Use Case Diagram | Hewad | 14 | 2 | W5 | W5 | Completed |
| 16 | Analysis | Write Use Case Descriptions | Detailed use cases | Hewad | 15 | 3 | W5 | W5 | Completed |
| 17 | Analysis | Create Activity Diagrams | Activity Diagrams | Ehsanullah | 16 | 3 | W5 | W6 | Completed |
| 18 | Analysis | Create Class Diagram | Class Diagram | Haroon | 14,16 | 3 | W5 | W6 | Completed |
| 19 | Analysis | Create Sequence Diagrams | Sequence Diagrams | Haroon | 18 | 3 | W6 | W6 | Completed |
| 20 | Database | Identify entities and attributes | Entity/attribute list | Haroon | 12,14 | 2 | W7 | W7 | Not Started |
| 21 | Database | Create ER Diagram | ER Diagram | Ahmadullah | 20 | 3 | W5 | W6 | Completed |
| 22 | Database | Normalize database design | Normalized schema | Haroon | 21 | 2 | W6 | W6 | Not Started |
| 23 | Design | Design system architecture | Architecture diagram | Ahmadullah | 18,21 | 2 | W6 | W6 | Completed |
| 24 | Design | Design navigation and wireframes | Wireframes | Ehsanullah | 15–17 | 4 | W6 | W7 | Not Started |
| 25 | Design | Design authentication and permissions | Access-control design | Ehsanullah + Hewad | 14,15 | 2 | W7 | W7 | Not Started |
| 26 | Design | Design vehicle and inventory screens | Vehicle UI | Ehsanullah | 24 | 3 | W7 | W7 | Not Started |
| 27 | Design | Design customer and reservation screens | Customer/reservation UI | Ehsanullah | 24 | 3 | W7 | W7 | Not Started |
| 28 | Design | Design sales, payment and report screens | Sales/payment/report UI | Ehsanullah | 24 | 4 | W7 | W8 | Not Started |
| 29 | Implementation | Set up project structure and database | Working project/database | Haroon + Ehsanullah | 22–25 | 3 | W8 | W8 | Not Started |
| 30 | Implementation | Implement authentication and roles | Login/authorization | Hewad | 25,29 | 4 | W8 | W8 | Not Started |
| 31 | Implementation | Implement vehicle and inventory management | Vehicle/inventory module | Hewad + Ahmadullah | 26,29 | 6 | W8 | W9 | Not Started |
| 32 | Implementation | Implement customer management | Customer module | Ahmadullah | 27,29 | 4 | W9 | W9 | Not Started |
| 33 | Implementation | Implement reservation management | Reservation module | Ahmadullah | 32 | 4 | W9 | W10 | Not Started |
| 34 | Implementation | Implement sales management | Sales module | Hewad + Ahmadullah | 31–33 | 6 | W9 | W10 | Not Started |
| 35 | Implementation | Implement payment management | Payment module | Haroon | 34 | 4 | W10 | W10 | Not Started |
| 36 | Implementation | Implement employee management | Employee module | Hewad | 30 | 3 | W10 | W10 | Not Started |
| 37 | Implementation | Implement reports/dashboard | Reports module | Ahmadullah+ Hewad | 31,34–36 | 4 | W10 | W11 | Not Started |
| 38 | Integration | Integrate frontend, backend and database | Integrated system | Ehsanullah + Haroon | 30–37 | 4 | W11 | W11 | Not Started |
| 39 | Testing | Prepare test cases | Test-case document | Ehsanullah | 38 | 2 | W11 | W11 | Not Started |
| 40 | Testing | Unit and module testing | Unit test results | Ehsanullah | 30–37 | 3 | W11 | W11 | Not Started |
| 41 | Testing | Integration and system testing | System test results | All | 38–40 | 3 | W11 | W12 | Not Started |
| 42 | Testing | Security, usability and validation testing | Quality report | Hewad | 41 | 2 | W12 | W12 | Not Started |
| 43 | Testing | Fix bugs and regression testing | Stable release | All | 41–42 | 3 | W12 | W12 | Not Started |
| 44 | Documentation | Update SRS and diagrams | Final SRS | Ahmadullah + All | 43 | 2 | W12 | W12 | Not Started |
| 45 | Documentation | Prepare final project report | Final report | Ahmadullah | 44 | 3 | W12 | W12 | Not Started |
| 46 | Presentation | Prepare presentation and demonstration | Slides/demo | All | 44–45 | 2 | W12 | W12 | Not Started |
| 47 | Presentation | Final review, submission and presentation | Submitted project | Ahmadullah + All | 46 | 1 | W12 | W12 | Not Started |

# 6. 12-Week Gantt Chart

| ID | Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Define problem and project idea | ■ |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Define project objectives | ■ |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Identify stakeholders and actors | ■ |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Define project scope and boundaries | ■ |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Prepare project chart and work plan | ■ |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Gather functional requirements | ■ | ■ |  |  |  |  |  |  |  |  |  |  |
| 7 | Gather non-functional requirements |  | ■ |  |  |  |  |  |  |  |  |  |  |
| 8 | Define business rules |  | ■ |  |  |  |  |  |  |  |  |  |  |
| 9 | Identify actors and use cases |  | ■ |  |  |  |  |  |  |  |  |  |  |
| 10 | Write Introduction and Overall Description |  | ■ | ■ |  |  |  |  |  |  |  |  |  |
| 11 | Write Specific Requirements |  |  | ■ | ■ |  |  |  |  |  |  |  |  |
| 12 | Write Data Requirements and Constraints |  |  |  | ■ |  |  |  |  |  |  |  |  |
| 13 | Define acceptance criteria |  |  |  | ■ |  |  |  |  |  |  |  |  |
| 14 | Review and finalize SRS |  |  |  | ■ |  |  |  |  |  |  |  |  |
| 15 | Create Use Case Diagram |  |  |  |  | ■ |  |  |  |  |  |  |  |
| 16 | Write Use Case Descriptions |  |  |  |  | ■ |  |  |  |  |  |  |  |
| 17 | Create Activity Diagrams |  |  |  |  | ■ | ■ |  |  |  |  |  |  |
| 18 | Create Class Diagram |  |  |  |  | ■ | ■ |  |  |  |  |  |  |
| 19 | Create Sequence Diagrams |  |  |  |  |  | ■ |  |  |  |  |  |  |
| 20 | Identify entities and attributes |  |  |  |  | ■ |  |  |  |  |  |  |  |
| 21 | Create ER Diagram |  |  |  |  | ■ | ■ |  |  |  |  |  |  |
| 22 | Normalize database design |  |  |  |  |  | ■ |  |  |  |  |  |  |
| 23 | Design system architecture |  |  |  |  |  | ■ |  |  |  |  |  |  |
| 24 | Design navigation and wireframes |  |  |  |  |  | ■ | ■ |  |  |  |  |  |
| 25 | Design authentication and permissions |  |  |  |  |  |  | ■ |  |  |  |  |  |
| 26 | Design vehicle and inventory screens |  |  |  |  |  |  | ■ |  |  |  |  |  |
| 27 | Design customer and reservation screens |  |  |  |  |  |  | ■ |  |  |  |  |  |
| 28 | Design sales, payment and report screens |  |  |  |  |  |  | ■ | ■ |  |  |  |  |
| 29 | Set up project structure and database |  |  |  |  |  |  |  | ■ |  |  |  |  |
| 30 | Implement authentication and roles |  |  |  |  |  |  |  | ■ |  |  |  |  |
| 31 | Implement vehicle and inventory management |  |  |  |  |  |  |  | ■ | ■ |  |  |  |
| 32 | Implement customer management |  |  |  |  |  |  |  |  | ■ |  |  |  |
| 33 | Implement reservation management |  |  |  |  |  |  |  |  | ■ | ■ |  |  |
| 34 | Implement sales management |  |  |  |  |  |  |  |  | ■ | ■ |  |  |
| 35 | Implement payment management |  |  |  |  |  |  |  |  |  | ■ |  |  |
| 36 | Implement employee management |  |  |  |  |  |  |  |  |  | ■ |  |  |
| 37 | Implement reports/dashboard |  |  |  |  |  |  |  |  |  | ■ | ■ |  |
| 38 | Integrate frontend, backend and database |  |  |  |  |  |  |  |  |  |  | ■ |  |
| 39 | Prepare test cases |  |  |  |  |  |  |  |  |  |  | ■ |  |
| 40 | Unit and module testing |  |  |  |  |  |  |  |  |  |  | ■ |  |
| 41 | Integration and system testing |  |  |  |  |  |  |  |  |  |  | ■ | ■ |
| 42 | Security, usability and validation testing |  |  |  |  |  |  |  |  |  |  |  | ■ |
| 43 | Fix bugs and regression testing |  |  |  |  |  |  |  |  |  |  |  | ■ |
| 44 | Update SRS and diagrams |  |  |  |  |  |  |  |  |  |  |  | ■ |
| 45 | Prepare final project report |  |  |  |  |  |  |  |  |  |  |  | ■ |
| 46 | Prepare presentation and demonstration |  |  |  |  |  |  |  |  |  |  |  | ■ |
| 47 | Final review, submission and presentation |  |  |  |  |  |  |  |  |  |  |  | ■ |

# 7. Major Milestones

| ID | Milestone | Target | Owner / Lead | Acceptance Condition |
| --- | --- | --- | --- | --- |
| M1 | Scope approved | W1 | Ahmadullah + All | Scope and boundaries agreed and recorded. |
| M2 | Requirements completed | W2 | Ahmadullah | Functional/non-functional requirements and business rules reviewed. |
| M3 | SRS completed | W4 | Ahmadullah + All | SRS reviewed, internally consistent and approved as baseline. |
| M4 | UML models completed | W6 | Hewad + Ehsanullah + Haroon | Use Case, Activity, Class and Sequence models completed and mutually consistent. |
| M5 | Database design completed | W6 | Ahmadullah | ERD, keys, relationships and normalization validated. |
| M6 | UI/design completed | W8 | Ehsanullah | Core navigation, wireframes and module screens designed. |
| M7 | Core implementation completed | W10 | Hewad + Haroon + Ahmadullah | Main approved modules implemented with database support. |
| M8 | Integrated system completed | W11 | Ehsanullah + Haroon | Frontend, backend and database communicate correctly. |
| M9 | Testing completed | W12 | All; Ehsanullah coordinates | Required tests executed and critical defects resolved. |
| M10 | Final submission | W12 | Ahmadullah + All | System, final report, documentation, source/database package and presentation submitted. |

# 9. Main Project Deliverables

| Deliverable | Phase | Expected Content | Target |
| --- | --- | --- | --- |
| Project Scope | Initiation | Problem, objectives, scope, boundaries and stakeholders | W1 |
| Project Chart | Planning | Tasks, dependencies, responsibilities, schedule, milestones, risks and completion criteria | W1 |
| SRS | Requirements | Complete Software Requirements Specification | W4 |
| Use Case Diagram | Analysis | Actors, use cases and relationships | W5 |
| Activity Diagrams | Analysis | Main system workflows | W5–W6 |
| Class Diagram | Analysis | Classes, attributes, methods and relationships | W5–W6 |
| Sequence Diagrams | Analysis | Interactions for key scenarios | W5-W6 |
| ER Diagram | Database | Entities, attributes, keys, relationships and cardinalities | W5–W6 |
| Architecture Design | Design | Application/database/component structure | W5-W6 |
| UI/Wireframes | Design | Main screens and navigation | W6–W8 |
| Database | Implementation | Tables, keys, constraints and sample data | W8 |
| Working System | Implementation | Implemented modules and workflows | W10–W11 |
| Testing Documentation | Testing | Test cases, results, defects and fixes | W11–W12 |
| Final SRS/Report | Documentation | Updated diagrams, screenshots and final documentation | W12 |
| Presentation | Presentation | Slides and live system demonstration | W12 |

# 10. Project Risks and Mitigation

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Requirements change late | High | Medium | Freeze the requirements baseline after SRS review and record approved changes. |
| Scope becomes too large | High | High | Keep excluded features outside the baseline unless formally approved. |
| Database design errors | High | Medium | Review ERD, keys, cardinalities and normalization before implementation. |
| Integration problems | High | Medium | Integrate modules incrementally rather than waiting until the end. |
| Insufficient testing time | High | Medium | Prepare test cases early and reserve W11–W12 for QA and fixes. |
| Unequal team workload | Medium | Medium | Use the responsibility matrix and review progress regularly. |
| Loss of project files | High | Low | Use version control and regular backups. |

# 11. Project Completion Criteria

All approved functional requirements are implemented or formally documented as deferred.

Role-based access works for Administrator, Manager and Salesperson as specified by the SRS.

Vehicle, inventory, customer, reservation, sales, payment, employee and reporting modules are integrated.

Database relationships and constraints are implemented consistently with the ER diagram.

The final UML diagrams and SRS reflect the implemented system.

Required functional and non-functional tests are executed and critical defects are resolved.

Final report, screenshots, source code, database and presentation materials are prepared.

Excluded features remain outside the baseline unless an approved change is documented.

# 12. SRS-to-Project-Chart Traceability

| SRS Area | SRS Reference | Project Tasks | Responsible |
| --- | --- | --- | --- |
| Authentication & Authorization | FR-AUTH-01–07 | 25, 30, 40–43 | Hewad + Ahmadullah |
| Vehicle Management | FR-VEH-01–08 | 26, 31, 40–43 | Hewad + Haroon |
| Inventory/Search | FR-INV-01–05 | 26, 31, 37, 40–43 | Hewad + Haroon + Ahmadullah |
| Customers | FR-CUS-01–06 | 27, 32, 40–43 | Hewad |
| Reservations | FR-RES-01–06 | 27, 33, 40–43 | Hewad |
| Sales | FR-SAL-01–09 | 28, 34, 40–43 | Hewad + Ahmadullah |
| Payments | FR-PAY-01–07 | 28, 35, 40–43 | Haroon |
| Employees | FR-EMP-01–05 | 36, 37, 40–43 | Ahmadullah + Haroon |
| Reports | FR-REP-01–08 | 28, 37, 40–43 | Ahmadullah |
| NFRs | NFR-PERF through NFR-PORT | 7, 23–25, 39–43 | Ahmadullah + Ehsanullah + All |
| Data Requirements | SRS Section 5 | 12, 20–22, 29, 38, 41–43 | Haroon + Ahmadullah |
| Acceptance Criteria | SRS Section 7 | 13, 39–43, 47 | Ahmadullah + All |

# 13. Final Project Structure

Project Initiation → problem, objectives, stakeholders, scope

Project Planning → project chart, team responsibilities, schedule, risks

Requirements Engineering → FRs, NFRs, actors, use cases, business rules

SRS → complete requirements baseline and acceptance criteria

System Analysis → Use Case, Activity, Class and Sequence models

Database Design → entities, attributes, ERD, normalization

System/UI Design → architecture, navigation, permissions, wireframes

Implementation → authentication, vehicles, inventory, customers, reservations, sales, payments, employees, reports

Integration → frontend + backend + database

Testing → unit, integration, system, security, usability, validation and regression

Documentation → final SRS, diagrams, report and screenshots

Presentation & Submission → demonstration and final submission

# 14. Final Consistency Rules

The SRS defines what the system must do; the project chart defines how the team organizes and schedules the work.

The project chart must not introduce a baseline feature absent from the approved SRS unless a change is formally approved.

Every implementation module traces to SRS requirements.

Every milestone owner is aligned with the corresponding detailed task owner/lead.

The Gantt chart exactly follows the Start/End weeks in the detailed schedule.

Shared QA does not mean every member owns every development task.